“WE WILL MAKE IT FOR YOU”

Company Profile

Business Description

Events are something that Solana’s Events Company cherishes, is enthusiastic about, and treats as if it were their own. The company are able to surpass client expectations thanks to the company’s passion and dedication as well as the expertise of our in-house event specialists.

Understanding the aspirations of our clients is a top priority for us, and we collaborate with them to create an event that is one-of-a-kind and memorable. Rarely do the company only see a client once since the majority of Solana’s clients return time and time again, the company have a good relationship to its valued clients.

Solana’s Events Company can offer the appropriate assistance whether you need to improve client relationships, integrate new employees, jump-start learning and development, participate in team building, celebrate weddings and birthdays or simply host a party.

The company take pride in providing top-notch service to all of our clients, both large and small.

Company Logo and Tagline

The semi circle of the logo represent the importance of events that we are handling because we want to assure that our  customers  are in good hands.

As you can observe, the word Solana is presented elegantly because the company believes that in every event the company can bring out elegance in any form.

The logo is also made simple because the company wanted to show that simplicity is beauty.

“WE WILL MAKE IT FOR YOU”

“WE WILL MAKE IT FOR YOU” This is our tagline inspired by the tagline of  BDO we find ways but for us, the company wants to assure the client that we will make sure the the dream event they wanted will surely happen because Solana’s Events Company will make it for them.

Vision Statement

To be the best event management company in the country that focuses on the distinctiveness and uniqueness of each event and providing high quality service.

Mission Statement

To guarantee client fulfillment and loyalty while we produce customized, one-of-a-kind experiences that go above and beyond client expectations, forge strong bonds with clients and host remarkable events.

Objectives

- To create quality, memorable, and budget friendly event plans.

- To provide clients satisfaction and to help them save their precious time and money..

- To manage every event with excellence and elegance.

- To execute clients plans and wants for the event.

- To establish good relationship with client and create loyalty by providing satisfaction in every event.

- Proposal Letter to the  Client

3 March, 2023

Ms. Anne Lorraine Lagmay

Admin Staff

San Leonardo National High School

San Bartolome, San Leonardo, Nueva Ecija

0936-292-3591

Dear Ms. Lagmay,

Greetings in the name of the Lord!

Thank you for entrusting Solana’s Events Company with such important day in your school. Solana’s Events Company is thrilled to be part of the Commencement Exercises of your prestigious school. The business, one of the greatest event planners, will make sure to provide great offers for you. Since the business has been operating in the industry for almost twelve years, with the said years of experience Solana’s Events Company has proven it’s worth in organizing such events. We have been consistent event manager in Mallorca National High School, Mambangnan National High School and Tagumpay Nagano High School. The company is also one of the most recommended events specialist through the previous client’s feedback in organizing a successful Commencement Exercises.

You mentioned during our initial meeting, the 125th Commencement Exercises theme for year 2023-2024 is “Defying Odds: Achieving Holistic Excellence” and will be held on the 9th of June 2023 at Nueva Ecija University of Science and Technology Gymnasium with 400 guests’ with a budget allocation of P 300,000.00.

Rest assured that the company will do all possible to please you and your guests and make the event memorable. Solana's Events Company is in charge of providing all the goods and services needed for the event, from initial planning and conceptualization to final implementation. You can contact us using the details at the bottom of this letter for any clarifications or further information regarding the event. Thank you, and enjoy your day!

Considering this proposal, Solana’s Events company would like to set an appointment to meet to fully discuss the concept and the contract. For questions and clarifications in regards to this proposal, feel free to contact our company with the contact number and email attached in this letter and we are looking forward to work with you.

Thank you.

Respectfully yours,

April Joy Uberas

Event Manager

Solana’s Events Company

- Proposal Letter to the Suppliers

10 March, 2022

Mrs. Janet A. Caymo

Owner

Foodelights

San Leonardo, Nueva Ecia

09369065412

Dear Mrs. Caymo,

Greetings!

On June 9, 2023, the company, Solana’s Events Company, will oversee a Commencement Exercise with the theme “Defying Odds: Achieving Holistic Excellence” 400 attendees will be present at the event. At precisely 9:00 AM, the aforementioned event will be held at Nueva Ecia University of Science and Technology in Tambo Adorable, Nueva Ecija.

We would like to let you know that your shop has been selected as a provider of snacks and fruits in the said event. Regarding this, we would want to get a price quote on your programs. The items we require are as follows:

- Snacks

- Sandwhich

- Cupcakes

- Chips

- Bottled Water

- Fruits

- Grapes

- Orange

You can contact us using the details at the bottom of this letter if you have any questions about this matter. Let's join forces to make this occasion memorable. Thank you, and enjoy your day!

Respectfully yours,

APRIL JOY UBERAS

Event Manager

Solana’s Events Company

EVENT BRIEF

| Contact Coordinator | Ms, April Joy Uberas Solana’s Events Company Mallorca, San Leonardo, Nueva Ecija 09157303451 solanaseventscompany@gmail.com |
| --- | --- |
| Event | 120th Commencement Exercise |
| Name of Event | “Defying Odds: Achieving Holistic Excellence” |
| Purpose | To celebrate the hardwork of students and parents. |
| Theme | “Defying Odds: Achieving Holistic Excellence” |
| Motif/Dress Code | Filipiniana and Barong |
| Client | Ms. Anne Lorraine Lagmay |
| Day/Date | Friday/ 9 June 2023 |
| Time | 9:00 - 12:00 NN |
| Budget Allocation | 400,000 |
| Venue and Location | Nueva Ecija University of Science and Technology Gymnasium |
| No. of Guest | 400 |
| Guests/Participants | Faculty, Students and Faculty |
| No. Of Staff | 10 |
| Invitation | It will distributed on week before the event. |
| Permit | It will be secured from Municipal IATF. |
| Parking Access | Beside the NEUST Gymnasium |
| Directional Signage | Parking Space, Entrance and Exit, Comfort Room and Emergency Exit. |
| Audio Visual Set- Up | Sound System, Microphone and Projector. |
| Set- Up | Refer to Gymnasium floor plan. |

EVENT TIMELINE

| ACTIVITIES | DATE |
| --- | --- |
| Contract Signing to Client (Initial Payment of 50 %) | March 5, 2023 |
| Planning and Preparation | March 12, 2023 - June 5, 2023 |
| Selection of Suppliers | March 15, 2023- March 29, 2023 |
| First Meeting with Suppliers | April 2, 2023 |
| Sending of Contract to Suppliers | April 7, 2023 |
| Contract Signing to Suppliers | April 8, 2023 - April 10, 2022 |
| Second Meeting with Client | April 13, 2023 |
| First Meeting with Working Committee | May 5, 2023 |
| Second Meeting with Suppliers (Payment) | May 10, 2023 |
| Special Permits (IATF) | May 16, 2023 |
| Final Meeting with Client (Payment for 50% remaining) | May 18, 2023 |
| Final Meeting with Working Committee | June 5, 2023 |
| Ingress | June 9, 2023 6AM-9AM |
| Engress | June 9, 2023 2PM-4PM |
| Post Meeting with Client | June 12, 2023 |
| Post Meeting with Working Committee | June 13, 2023 |

BUDGET PROPOSAL

|  | AMOUNT |
| --- | --- |
| VENUE | P 30,000 |
| Space for graduation |  |
| Parking lot & space freight |  |
| Generator |  |
| Projector & Screen |  |
| Stage |  |
| CHAIRS AND TABLES | 15,500 |
| Table and Chairs |  |
| Red Carpet |  |
| Linen, table napkins & skirting, Knives |  |
| VENUE DECORATIONS | 10,000 |
| Table Sep Up |  |
| Flowers |  |
| VIDEO/PHOTOGRAPHER | 12,000 |
| 3 Photographer |  |
| 1 Videographer |  |
| Photobooth |  |
| Raw & edited pictures |  |
| - Solo Stage Photo |  |
| - With Parent Photo |  |
| - Live and Recorded Graduation |  |
| - PRINTING SERVICES | 10,800 |
| - Invitations |  |
| - Tarpauline |  |
| - Diploma and Special Awards |  |
| LIGHTS & SOUNDS | 15,000 |
| Lights for Venue |  |
| Proector |  |
| Spotlight |  |
| Sound system |  |
| Sound generator & electrician |  |
| Wireless microphone |  |
| MEDALS AND RIBBONS | 10,000 |
| Medal |  |
| Boxes |  |
| Laces |  |
| Ribbons |  |
| GOWN AND SUITS | 80,0000 |
| Toga Gowns |  |
| Toga Cap |  |
| GUEST SPEAKER | 15,000 |
| Mr. Prince Matthew Baruilla |  |
| OTHER ITEMS | 8,000 |
| Souvenirs |  |
| Balloons |  |
| Special Paper |  |
| FOOD | 15,000 |
| Snacks |  |
| Fruits |  |
| Bottled Water |  |
| FIRST AID KIT | 5,000 |
| TOTAL EXPENSES | P 226, 300 |
| CONTINGENCY FUND: 15 % | 33,945 |
| TOTAL EXPENSES AND CONTINGENCY FUND | 260,245 |
| PROFESSIONAL FEES: 15 % | 39,036.75 |
| GRAND TOTAL | 299,281.75 |

FLOOR PLAN

STAGE

TOILET

STUDENTTT

MEDICS

PARKING

SOUND SYSTEM

FACULTY

SNACKS AREA

PARENTS

PROJECTOR

PHOTOBOOTH

EMERGENCY EXIT

EXIT

ENTRANCE

WORKING COMMITTEES

| STAFF | AREA | REQUIREMENTS | FUNCTION |
| --- | --- | --- | --- |
| Staff 1 | Front Stage | Program Flow | Master of the Ceremony |
| Staff 2 | Entrance | List of Attendees Lei Necklace | Welcoming the Attendees |
| Staff 3 | Entrance | List of Attendees Floor Plan | Assisting the attendees to their assigned seat. |
| Staff 4 | Table and Chair Area | Floor Plan | Arranging table seating. |
| Staff 5 | Medics Area | IATF Protocol | Reminding attendees to wear facemask and maintain social distancing. |
| Staff 6/Technical | Sound System | Program Flow | Operator and Technician |
| Staff 7 | Rest rooms | Cleaning Materials | Maintaining the cleanliness of the restrooms. |
| Staff 8/ Traffic Enforcer | Parking Area | Parking Signage Whistle | Assisting guest in parking area. |
| Staff 9/Security | Shoreline | Safety and Security Items | Secure the safety of the Attendees |
| Staff 10 | Snacks Area | Snacks, Water and Fruits | Assigned to distribute snacks. |

LIST OF SUPPLIERS

| COMPANY NAMES | SERVICES |
| --- | --- |
| NEUST Gymnasium | Venue |
| 3K Designs | Table and Chairs Rental |
| Foodelights | Snacks, Fruits and Water |
| Local Photography | Photos and Videos |
| AD Lights and Sounds | Lights and Sounds |
| Uniprint Nueva Ecija | Printing Services |
| Juanita’s Gift Shop | Souvenir Supplier |
| Party Den Blooms & Event | Venue and Stage Decorations |
| Matundan Trading | Medals and Ribbons |
| MELLE’S Toga Rental | Toga Gown and Cap |
| Red Cross | First Aid Kit |

LIST OF ALTERNATIVE SUPPLIERS

| COMPANY NAMES | SERVICES |
| --- | --- |
| San Leonardo Gymnasium | Venue |
| Shylla’s Special Events Botique | Table and Chairs Rental |
| Baked by Kate | Snacks, Fruits and Water |
| Heartnet Enterprises | Photos and Videos |
| Sound Stream Mobile | Lights and Sounds |
| Almers Advertising & Printing Supplies | Printing Services |
| Jowies Gift Shop | Souvenir Supplier |
| ERIC & LARA’S TROPHIES AND MEDALS | Medals and Ribbons |
| Design and Decorations Birthday Party, Debut, Wedding | Venue and Stage Decorations |
| Ethel | First Aid Kit |

- \

- DETAILED BUDGET PROPOSAL

Event: Wedding					Client: Mr, Prince Matthew Barquilla

Budget Alloted: P400,000				Attendees: 150 pax

Day/Date/Time: Sunday, June 18, 2023, 9:00 AM-3:00 PM

| VENDOR/LOCATION | SERVICES | PARTICULARS |  | AMOUNT | TOTAL |
| --- | --- | --- | --- | --- | --- |
| NEUST Gymnasium | Venue | Space for graduation |  | P20,000 |  |
|  |  | Parking lot & space freight |  | 5,000 |  |
|  |  | Generator |  | 2,000 |  |
|  |  | Projector & Screen |  | 1,000 |  |
|  |  | Stage |  | 2,000 |  |
| P30,000 |  |  |  |  |  |
| 3K Designs | Table and Chairs Rental | Table and Chairs |  | 12,000 |  |
|  |  | Red Carpet |  | 1,500 |  |
|  |  | Linen, table napkins & skirting, Knives |  | 2,000 |  |
| 15,500 |  |  |  |  |  |
| Party Den Blooms & Event | Venue and Stage Decorations | Table Sep Up |  |  | 5,000 |
|  |  | Flowers |  |  | 2,000 |
|  |  | Florist |  |  | 3,000 |
| 10,000 |  |  |  |  |  |
| Local Photography | Photos and Videos | 3 Photographer |  |  |  |
|  |  | 1 Videographer |  |  |  |
|  |  | Photobooth |  |  |  |
|  |  | Raw & edited pictures |  |  |  |
|  |  | - Solo Stage Photo - \With Parent Photo - Live and Recorded Graduation |  |  |  |
| 12,000 |  |  |  |  |  |
| Uniprint Nueva Ecija | Printing Services | Invitations |  | 6,000 |  |
|  |  | Tarpauline |  | 1,500 |  |
|  |  | Diploma and Special Awards |  | 13,000 |  |
| 20,800 |  |  |  |  |  |
| AD Lights and Sounds | Lights and Sounds | Lights for Venue |  |  |  |
|  |  | Proector |  |  |  |
|  |  | Spotlight |  |  |  |
|  |  | Sound system |  |  |  |
|  |  | Sound generator & electrician |  |  |  |
|  |  | Wireless microphone |  |  |  |
| 15,000 |  |  |  |  |  |
| Matundan Trading | Medals and Ribbons | Medal |  | 5,000 |  |
|  |  | Boxes |  | 2,000 |  |
| \ |  | Laces |  | 1,500 |  |
|  |  | Ribbon |  | 1,500 |  |
| 10,000 |  |  |  |  |  |
| MELLE’S Toga Rental | Toga Gown and Cap | Gowns Cap |  |  |  |
| 80,000 |  |  |  |  |  |
| Mr. Prince Matthew Barquilla | Guest Speaker | Speech |  |  |  |
| 15,000 |  |  |  |  |  |
| Juanita’s Gift Shop | Souvenir Supplier | Souvenirs |  | 7,000 |  |
|  |  | Balloons |  | 500 |  |
|  |  | Special Paper |  | 500 |  |
| 8,000 |  |  |  |  |  |
| Foodelight | Snacks | Snacks |  | 8,000 |  |
|  |  | Fruits |  | 4,000 |  |
|  |  | Bottled Water |  | 3,000 |  |
| 15,000 |  |  |  |  |  |
| Red Cross | First Aid Kit | - Alcohol |  |  |  |
|  |  | - Gauze |  |  |  |
|  |  | - Band Aid |  |  |  |
|  |  | - Cotton |  |  |  |
|  |  | - Betadine |  |  |  |
| 5,000 |  |  |  |  |  |
| TOTAL EXPENSES |  |  | P 226, 300 |  |  |
| CONTINGENCY FUND: 15 % |  |  | 33,945 |  |  |
| TOTAL EXPENSES AND CONTINGENCY FUND |  |  | 260,245 |  |  |
| PROFESSIONAL FEES: 15 % |  |  | 39,036.75 |  |  |
| GRAND TOTAL |  |  | 299,281.75 |  |  |

DETAILED PROGRAM FLOW

| TIME | FLOW | ALLOTED TIME | IN CHARGE | FUNCTION | REQUIREMENTS |
| --- | --- | --- | --- | --- | --- |
| 9:00 – 9:20 | Arrival of Participants & Guests ( Wedding Ceremony) | 20 minutes | Staff 2 and 5 | - Welcoming the Guest - Reminding guests to wear facemask and maintain social distancing. | - List of Attendees - IATF Protocol - Secure the following: - Program - Participants - Program Host - Video/Photographer - Sound System - Projector - Traffic Enforcer - Staffs - Technical Staff - Security |
| 9:20-9:40 | Processional | 20 minutes | Staff 3 | - Assist the attended to their assigned seat. | - Presents the Guests,Faculty and Staff, Parents and Graduates - Play Graduation March Song - Ensures that social distancing and other health protocols are strictly follows. - Floorplan - Program - Participants - Program Host - Video/Photographer - Sound System - Projector |
| 9:40-9:42 | Doxology | 2 minutes | Dance Club Staff 6 | - Operator and Technician | - Perform the hymn of praises - Operates the sound system - Music - Projector - Stage |
| 9:42-9:44 | Philippine National Anthem | 2 minutes | Glee Club | - Singing of the Philippine National Anthem | - Microphones - Minus one - Philippne Flag |
| 9:44-9:46 | SLNHS Hymn | 2 minutes | Glee Club and Students | - Singing of the CIC Hymn | - Microphones |
| 9:46-9:49 | Welcome Message | 3 minutes | Master of the Ceremony Salutatorian | - Officially welcoming the Guests, Parents and Graduates to the Program | - Microphone - List of Guests - Welcome message |
| 9:49-9:54 | Inspirational/Congratulatory Message from LGU | 5 minutes | Master of the Ceremony Mayor,Brgy. Captain or Representative | - Give an inspirational/ congratulatory message to graduates and parents coming from LGU Officials. | - Microphone - Message - Mayor - Barangay Captain |
| 9:54-9:56 | Presentation of Candidates for Graduation | 2 minutes | Master of the Ceremony SLNHS School Principal | - Introduce the President of the School - Presents the number of graduates boys and girls. | - Microphone - Number List of graduates girls and boys |
| 9:56-10:06 | Confirmation of the Graduates & Message of the School Division Superintendent | 10 minutes | SDS or his/her Authorized Representative | - Congratulatory Message and a Confirmation of the Graduates for the School Year 2023-2024 | - Microphone - Number List of graduates girls and boys |
| 10:06-10:11 | Preparation for Distribution of Diplomas Giving snacks and water to attendees | 5 minutes | SLNHS Faculty Staff 10 | - Prepared the diplomas given to the students | - Diplomas - Table - Snacks - Bottled Water |
| 10:11-10:56 | Distribution of Diplomas | 45 minutes | SLNHS Faculty and Staff Guest Speaker LGU Officials Master of the Ceremony Photographer/Videographe | - Assisting the people involve in the Distribution of Diplomas - Guest will give the diplomas to graduates. - Students with their parents will go to stage to claim the diploma. - Calling of names in the invitation program each section. | - Graduates and Parents - Diplomas - Microphone - Sound System - Camera |
| 10:56-10:59 | Introduction of the Guest Speaker | 3 minutes | Faculty President | - Short background introduction and warm welcome to invited guest speaker. | - Microphone - Music |
| 10:59-11:19 | Message | 20 minutes | Guest Speaker | - Giving of inspirational message to graduates. | - Microphone |
| 11:19-11:21 | Presentation of Academic Honors and Awards | 2 minutes | SLNHS Faculty and Staff Guest Speaker LGU Officials Master of the Ceremony | - Giving of Academic Honors and Awards to selected students. - Assisting the parents and graduates as they claim the awards. | - Medals - Certificates - List of selected students - Tables - Microphone - Music - Photographer/videographer - Technical staff |
| 11:21-11:26 | Words of Gratitude | 5 minutes | Valedictorian | - Giving of words of gratitude/sharing experiences in the years in SLNHS. | - Microphone |
| 11:26-11:29 | Graduation Song | 3 minutes | Graduates | - Singing of graduation song. | - ”The Climb” - Minus one - Lyrics - Microphone - Sound System |
| 11:29-11:34 | Acknowledgement | 5 minutes | SLNHS School Principal | - Thank you message from the School President | - Microphone |
| 11:34-12:00 | Recessional and Picture Taking | 26 minutes | Faculty and Staff Photographer Staff 5 and 9 | - Falling in line to exit. - Make sure that health protocols are strictly - follows as they leave the venue - . - Ensures the safety of the guests | - Camera - Signages - IATF Protocol - Graduates and Parents |

- RISK MANAGEMENT

| RISK | CAUSE | CONTINGENCY PLAN |
| --- | --- | --- |
| Power Outages | Caused by faulty wires Power line damage | Stand by generator |
| Sound System Failure | Technical failures | Stand by event staff and electrician |
| Unexpected Accident | Minor injuries Harm inside the venue | Stand by medics, First Aid Kit, and ambulance |
| Absence of Officials/Staff | Emergency Matter/Sick | Inform the Coordinator/Call a substitute ahead of time |
| Guests failure to arrive on time | Other official business | Continue the event program Call/Tell other authorized person to have a message on behalf. |
| Power Outages | Caused by faulty wires Power line damage | Stand by generator |