“MAKE YOUR OCCASION LIVE YOUR EXPECTATION”

Company Profile

Business Description

Occa Events Company is a full service professional event planning company that specializes, conceptualizes, plan an  events and occasions such as weddings, parties, conventions and corporate meetings. We are one of the best and capable when it comes to these events, we make sure what our client's dreams and desire come in reality.

Occa Events Company composed of professional consultant and coordinators that are all well-experienced and passionate, who works alongside our clients from concept to completion, to give them a unique and memorable event.

As one of the best companies, Occa Events Company works with passion and dedication that enables us to exceed client's expectations.

Company Logo and Tagline

The gold lining of the logo represent the importance of events that we are handling because we want to assure that our  customers  are in good hands.

As you can observe, the letter A in the end of the word Occa is bigger than the sizes of other letters because it represent the words: Assuring an Astonishing Aftermath.

The logo is also made simple and elegant because we wanted to make the customer feel through the logo that even simplicity can give elegance.

“MAKE YOUR OCCASION LIVE YOUR EXPECTATION”

“Make your Occasion live your expectation” This is our tagline inspired by the famous trend expectation vs reality. But to make things different, the event we will create will no longer need the versus because we will give you the best and you will get what you expect.

Vision Statement

To be the most trusted event management business in the Philippines, recognizes for its high level of service quality. To bring the most efficient methods for planning and creating once-in-a-lifetime events, with each event exceeding everyone's expectations, providing continuous growth of both staff and technology.

Mission Statement

To be the instrument in creating and producing  client’s events dream while saving their most precious time and money. To provide maximum satisfaction to our valuable costumers.

Objectives

- Experience the quality, memorable, and budget friendly event plans.

- Ensures the client's satisfaction in the outcome of the service.

- Manage all areas of events, from pre-planning through the event day and post- event activities.

- Showcase the client's preferences through creativity and innovations.

- Maintain good rapport with the client through updating and seeking approval about planning of events.

- Proposal Letter to the  Client

1 November, 2022

Mr. Prince Matthew Barquilla

Owner

PMB Corporation

San Leonardo, Nueva Ecia

09106895413

Dear Mr. Barquilla,

Greetings!

Thank you for entrusting Occa Events Company with such an important day in your life. The Occa Events Company is thrilled to take part in your forthcoming wedding. The business, one of the greatest event planners, will make sure to provide great offers for you. Since the business has been operating in the industry for almost ten years, Occa's has proven its value by going above and beyond to meet all of its clients' expectations and celebrate their important occasions with remarkable services Occa Events Company is one of the most reputable event management companies in the country based on the positive client feedback. The business will do everything in its ability to ensure that the upcoming event will result in the realization of your dreams..

You mentioned during our initial meeting that your wedding will take place on June 18, 2023, 9:00 AM with 150 guests and the theme "Our Love and His Will," at the Casa Granja Events Venue, with a budget allocation of P400,000.

Rest assured that the company will do all possible to please you and your guests and make the event memorable. Occa Events Company is in charge of providing all the goods and services needed for the event, from initial planning and conceptualization to final implementation. You can contact us using the details at the bottom of this letter for any clarifications or further information regarding the event. Thank you, and enjoy your day!

Respectfully yours,

APRIL JOY UBERAS

Event Manager

Occa Events Company

- Proposal Letter to the Suppliers

28 November, 2022

Mrs. Janet A. Caymo

Owner

Foodelights

San Leonardo, Nueva Ecia

09369065412

Dear Mrs. Caymo,

Greetings!

On June 18, 2023, the company, Occa Events Company, will oversee a wedding celebration with the theme "Our Love and His Will." 150 guests will be present at the event. At precisely 9:00 AM, the aforementioned event will be held at Casa Granja Events Venue in Gapan City, Nueva Ecija.

We would like to let you know that your shop has been selected as a provider of cupcakes and a three-layer fondant cake. Regarding this, we would want to get a price quote on your programs. The items we require are as follows:

3 Layer Fondat Cake

- White, Blue and Silver colors

- Fresh lavender, gilded leaves and faded pastel blooms

- Brush with mettalic gold

- Bride and Groom Topper

- Cupcakes

- Chocolate Flavor

- Vanilla Flavor

You can contact us using the details at the bottom of this letter if you have any questions about this matter. Let's join forces to make this occasion memorable. Thank you, and enjoy your day!

Respectfully yours,

APRIL JOY UBERAS

Event Manager

Occa Events Company

EVENT BRIEF

| Contact Coordinator | Ms, April Joy Uberas OccaEvents Company Mallorca, San Leonardo, Nueva Ecija 09157303451 occaeventscompany@gmail.com |
| --- | --- |
| Event | Wedding |
| Name of Event | “Our Love and His will” |
| Purpose | To celebrate the love and union of two different people. |
| Theme | Blue and White Formal Attire |
| Client | Mr. Prince Matthew Barquilla |
| Day/Date | Sunday/ 18 June 2023 |
| TIME |  |
| Church | 9:00 - 12:00 NN |
| Reception | 12:30 - 3:30 PM |
| Budget Allocation | 400,000 |
| VENUE AND LOCATION |  |
| Church | New Hope Baptist Church |
| Reception | Casa Granja Events Venue |
| No. of Guest | 150 |
| Guests/Participants | Family, Churchmates, Friends and Colleague |
| No. Of Staff | 10 |
| Invitation | It will distributed on month before the wedding. |
| Permit | It will be secured from Municipal IATF. |
| Parking Access | Church and Reception Venue’s Parking Area ¦(with signages) |
| Directional Signage | Parking Space, Entrance and Exit, Comfort Room and Emergency Exit. |
| Audio Visual Set- Up | Sound System, Microphone and Projector. |
| Set- Up | Refer to church and reception floor plan. |

EVENT TIMELINE

| ACTIVITIES | DATE |
| --- | --- |
| Contract Signing to Client (Initial Payment of 50 %) | November 3, 2022 |
| Planning and Preparation | November 10, 2022 - June 13, 2023 |
| Selection of Suppliers | November 28, 2022- December 12, 2022 |
| First Meeting with Suppliers | December 15, 2022 |
| Sending of Contract to Suppliers | December 20, 2022 |
| Contract Signing to Suppliers | December 21, 2022 - December 23, 2022 |
| Second Meeting with Client | December 26, 2022 |
| First Meeting with Working Committee | January 15, 2023 |
| Second Meeting with Suppliers (Payment) | February 18, 2023 |
| Special Permits (IATF) | February 20, 2023 |
| Final Meeting with Client (Payment for 50% remaining) | March 3, 2023 |
| Final Meeting with Working Committee | May 5, 2023 |
| Ingress | June 18, 2023 6AM-9AM |
| Engress | June 18, 2023 6PM-9PM |
| Post Meeting with Client | June 20, 2023 |
| Post Meeting with Working Committee | June 22, 2023 |

BUDGET PROPOSAL

|  | AMOUNT |
| --- | --- |
| VENUE | P 55,000.00 |
| Space for reception |  |
| Space for ceremony |  |
| Parking lot & space freight |  |
| Generator |  |
| Projector & Screen |  |
| Stage |  |
| CATERING SERVICES | 67,500 |
| Food: 150 pax |  |
| Dessert Buffet |  |
| Wine & Liquor |  |
| Lechon |  |
| Table & chairs |  |
| Linen, table napkins & skirting, Knives |  |
| Waiters |  |
| Table Sep Up |  |
| Tent |  |
| VIDEO/PHOTOGRAPHER | 25,000.00 |
| 3 Photographer |  |
| 1 Videographer |  |
| Full edited video |  |
| Raw & edited pictures |  |
| SDE |  |
| - Pre-nup photo shoot |  |
| - Files & footage on flash drive |  |
| - Photo album |  |
| - Free USB |  |
| LIGHTS & SOUNDS | 10,000.00 |
| Lights for Venue |  |
| Spotlight |  |
| Sound system |  |
| Sound generator & electrician |  |
| Wireless microphone |  |
| INVITATIONS | 6000.00 |
| CAKE | 15,000.00 |
| VENUE DECORATION | 28,400.00 |
| Florist |  |
| Flowers |  |
| Accessories |  |
| OTHER ITEMS | 22,500.00 |
| Souvenirs |  |
| Balloons |  |
| Special Paper |  |
| MAKE UP & HAIR STYLIS (PACKAGE) | 15,000.00 |
| ATTIRE | 30,000.00 |
| Bridal Gown |  |
| Grooms Tuxedo |  |
| Bridesmaid (5) |  |
| Groomsmen (5) |  |
| Maid of Honor |  |
| Best Man |  |
| Flower Girl (3) |  |
| Bearers (3) |  |
| BRIDAL CAR | 3,000.00 |
| HOTEL | 14,000.00 |
| 7Days |  |
| JEWELRY | 10,000.00 |
| Wedding Ring Paired |  |
| TOTAL EXPENSES | P 301,400.00 |
| CONTINGENCY FUND: 15 % | 45,200 |
| TOTAL EXPENSES AND CONTINGENCY FUND | 346,600 |
| PROFESSIONAL FEES: 15 % | 51,990 |
| GRAND TOTAL | 398,590 |

FLOOR PLAN

WORKING COMMITTEES

| STAFF | AREA | REQUIREMENTS | FUNCTION |
| --- | --- | --- | --- |
| Staff 1 | Front Stage | Program Flow | Master of the Ceremony |
| Staff 2 | Entrance | List of Invitees | Welcoming the Guest |
| Staff 3 | Entrance | List of Invitees | Assisting the guest and sponsors to their assigned seat. |
| Staff 4 | Table and Chair Area | Floor Plan | Arranging table seating. |
| Staff 5 | Medics Area | IATF Protocol | Reminding guests to wear facemask and maintain social distancing. |
| Staff 6/Technical | Sound System | Program Flow, List of requested musics. | Operator and Technician |
| Staff 7 | Rest rooms | Cleaning Materials | Maintaining the cleanliness of the restrooms. |
| Staff 8/ Traffic Enforcer | Parking Area | List of Invitees | Assisting guest in parking area. |
| Staff 9/Security | Shoreline | Safety and Security Items | Secure the safety of the Guests |
| Staff 10 | Venue/Exit and Emergency Exit | Program Flow, List of Invitees, Floor Plan, List and contact of supplier. | Assigned to manage any unforeseen event. |

LIST OF SUPPLIERS

| COMPANY NAMES | SERVICES |
| --- | --- |
| Casa Granja Events Venue, Inc. | Reception & Ceremony |
| Flairs Catering Services | Catering |
| Local Photography | Photos and Videos |
| ENO lights and sound systems | Lights and Sounds |
| Invitations for less | Invitations |
| Foodelights | Wedding Cake and Cupcake Supplier |
| Juanita’s Gift Shop | Souvenir Supplier |
| Party Den Blooms & Event | Venue and Stage Decorations |
| Makeup Artistry by Matthew Ng | Make Up and Hair Style |
| Rene Vicencio Bridal Shop | Wedding Dress |
| Carbnb Booking Page | Bridal Car/ Transportation |
| Camp Paraiso Hotel and Resort | Honeymoon |
| Unisilver | Jewelry |

LIST OF ALTERNATIVE SUPPLIERS

| COMPANY NAMES | SERVICES |
| --- | --- |
| Chrishel’s Catering @ Bahay Kawayan Resort | Reception & Ceremony |
| Server’s Catering Services | Catering |
| AJ Prints and Videos | Photos and Videos |
| Soundbox Sound System | Lights and Sounds |
| Almers Advertising & Printing Supplies | Invitations |
| Haezzel’s Cups n’ Cakes | Wedding Cake and Cupcake Supplier |
| Jowies Gift Shop | Souvenir Supplier |
| Design and Decorations Birthday Party, Debut, Wedding | Venue and Stage Decorations |
| Margaux Make up Artistry | Make Up and Hair Style |
| Ate Malou’s Bridal Gown and Barong | Wedding Dress |
| Nick Motorcycle Gallery | Bridal Car/ Transportation |
| Marquez Residencia | Honeymoon |
| Ricel’s Jewellery | Jewelry |

- \

DETAILED BUDGET PROPOSAL

Event: Wedding					Client: Mr, Prince Matthew Barquilla

Budget Alloted: P400,000				Attendees: 150 pax

Day/Date/Time: Sunday, June 18, 2023, 9:00 AM-3:00 PM

| VENDOR/LOCATION | SERVICES | PARTICULARS |  | AMOUNT | TOTAL |
| --- | --- | --- | --- | --- | --- |
| Casa Granja Events Venue, Inc. | Venue | Space for reception |  | P20,000 |  |
|  |  | Space for ceremony |  | 20,000 |  |
|  |  | Parking lot & space freight |  | 10,000 |  |
|  |  | Generator |  | 2,000 |  |
|  |  | Projector & Screen |  | 1,000 |  |
|  |  | Stage |  | 2,000 |  |
| P55,000 |  |  |  |  |  |
| Flairs Catering Services | Catering Services | Food: 150 pax x 200 |  | 37,000 |  |
|  |  | Dessert Buffet |  | 4,500 |  |
|  |  | Wine & Liquor |  | 10,000 |  |
|  |  | Lechon |  | 6.000 |  |
|  |  | Table & chairs Linen, table napkins & skirting, Knives Waiters Table Sep Up Tent |  | 10,000 |  |
| 67,500 |  |  |  |  |  |
| Local Photography | Video/Photographer | 3 Photographer |  |  |  |
|  |  | 1 Videographer |  |  |  |
|  |  | Full edited video |  |  |  |
|  |  | Raw & edited pictures |  |  |  |
|  |  | SDE |  |  |  |
|  |  | - Pre-nup photo shoot |  |  |  |
|  |  | - Files & footage on flash drive |  |  |  |
|  |  | - Photo album |  |  |  |
|  |  | - Free USB |  |  |  |
| 25,000 |  |  |  |  |  |
| ENO lights and sound systems | Lights & Sounds | Lights for Venue |  |  |  |
|  |  | Spotlight |  |  |  |
|  |  | Sound system |  |  |  |
|  |  | Sound generator & electrician |  |  |  |
|  |  | Wireless microphone |  |  |  |
| 10,000 |  |  |  |  |  |
| Invitations for less | Invitations | Invitations 75pcs x 80php |  | 6,0000 |  |
| 6,000 |  |  |  |  |  |
| Edna’s Cakeland | Cake | 3 layers Fondant Cake |  | 10,000 |  |
|  |  | Cupcakes 100pcs x 50php |  | 5,000 |  |
| 15,000 |  |  |  |  |  |
| Juanita’s Gift Shop | Souvenirs | Favors 150pcs x 150php |  | 22,500 |  |
| 22,500 |  |  |  |  |  |
| Party Den Blooms & Event | Venue Decoration | Florist |  | 10,000 |  |
|  |  | Fresh Flowers |  | 2,400 |  |
|  |  | Artificial Flowers |  | 8,000 |  |
|  |  | Accessories |  | 8,000 |  |
| 28,400 |  |  |  |  |  |
| Makeup Artistry by Matthew Ng | Make Up and Hair Stylist | Complete Package |  | 15,000 |  |
| 15,000 |  |  |  |  |  |
| Rene Vicencio Bridal Shop | Attire | Package |  | 30,000 |  |
|  |  | - Bridal Gown |  |  |  |
|  |  | - Grooms Tuxedo |  |  |  |
|  |  | - Bridesmaid (5) |  |  |  |
|  |  | - Groomsmen (5) |  |  |  |
|  |  | - Maid of Honor |  |  |  |
|  |  | - Best Man |  |  |  |
|  |  | - Flower Girl (3) |  |  |  |
|  |  | - Bearers (3) |  |  |  |
| 30,000 |  |  |  |  |  |
| Carbnb Booking Page | Transportation | - Bridal Car |  | 3,000 |  |
| 3,000 |  |  |  |  |  |
| Camp Paraiso Hotel and Resort | Hotel | - 1 Room for 7 days |  | 14,000 |  |
| 14,000 |  |  |  |  |  |
| Unisilver | Jewelry | - Wedding Ring Paired |  | 10,000 |  |
| 10,000 |  |  |  |  |  |
| TOTAL EXPENSES |  |  | P 301,400.00 |  |  |
| CONTINGENCY FUND: 15 % |  |  | 45,200 |  |  |
| TOTAL EXPENSES AND CONTINGENCY FUND |  |  | 346,600 |  |  |
| PROFESSIONAL FEES: 15 % |  |  | 51,990 |  |  |
| GRAND TOTAL |  |  | 398,590 |  |  |

DETAILED PROGRAM FLOW

| TIME | FLOW | ALLOTED TIME | IN CHARGE | FUNCTION | REQUIREMENTS |
| --- | --- | --- | --- | --- | --- |
| 9:00 – 9:55 | Arrival of Participants & Guests ( Wedding Ceremony) | 55 minutes | Staff 2 and 5 | - Welcoming the Guest - Reminding guests to wear facemask and maintain social distancing. | - List of Invitees - IATF Protocol - Secure the following: - Program - Participants - Program Host - Video/Photographer - Sound System - Projector - Traffic Enforcer - Officiant - Staffs - Technical Staff - Security |
| 9:55-10:05 | Entrance of the Guests | 10 minutes | Staff 3 | - Assisting the guest and sponsors to their assigned seat. | - List of Invitees - Floor Plan - Secure the following: - Guests - Microphones - Staffs - Security - Officiant |
| 10:05-10:20 | Prelude Processional Opening | 15 minutes | Officiant | Officiating the wedding ceremony | Secure the following: - Microphone - Program - Groom - Bride - Grooms/Bride Father - Videographer/Photographer |
| 10:20-10:30 | Rose Ceremony | 10 minutes | Officiant | Officiating the wedding ceremony | Secure the following: - Program - Microphone - Groom - Brides - Grooms Mother - Brides Mother - Photographer&Videographer |
| 10:30 – 10:3 | Readings | 5 minutes | Officiant | Officiating the wedding ceremony | Secure the following: - Microphone |
| 10:40-10:45 | Cord Ceremony | 5 minutes | Officiant | Officiating the wedding ceremony | Secure the following: - Microphone - Groom - Bride - Sponsors - Cord - Photographer& Videographer |
| 10:45-10:55 | Coin Ceremony | 10 minutes | Officiant | Officiating the wedding ceremony | Secure the following: - Microphone - Groom - Bride - Sponsors - Best Man - Arras/Coins - Photographer& Videographer |
| 10:55-11:00 | Removal of Veil and Cord | 5 minutes | Officiant | Officiating the wedding ceremony | Secure the following: - Microphone - Groom - Bride - Sponsors - Photographer & Videpgrapher |
| 11:00-11:15 | Exchange of Vows | 15 minutes | Officiant and Staff 6 | Officiating the wedding ceremony Operator and Technician | - Secure the following - Microphone - Groom - Bride - Photographer& - Videographer - Background Music “A Thousand Years” |
| 11:15-11:25 | Exchange of Rings | 10 minutes | Officiant and Staff 6 | Officiating the wedding ceremony Operator and Technician | - Secure the following: - Microphone - Groom - Bride - Best Man - Ring - Photographer & Videographer - Background Music “Perfect” |
| 11:25-11:30 | Blessing of the Hand | 5 minutes | Officiant | Officiating the wedding ceremony | - Secure the following - Microphone - Groom - Bride - Photographer& - Videographer |
| 11:30-11:40 | Lightning of the Unity Candle | 10 minutes | Officiant and Staff 6 | Officiating the wedding ceremony Operator and Technician | - Secure the following - Microphone - Groom - Bride - Candle - Photographer& - Videographer |
| 11:40-11:50 | Pronouncement | 10 minutes. | Officiant | Officiating the wedding ceremony | - Secure the following: - Microphone - Groom - Bride - Photographer& Videographer |
| 11:50-11:55 | Closing | 5 minutes | Officiant | Officiating the wedding ceremony | - Secure the following: - Microphone - Groom - Bride - Photographer& Videographer |
| 11:55-12:00 | The Kiss | 5 minutes | Officiant | Officiating the wedding ceremony | - Secure the following: - Microphone - Groom - Bride - Photographer& Videographer |
| 12:00-12:05 | Recessional | 5 minutes | Staff 6 | Operator and Technician | - Background Music “ All you need is Love” - Photographer& Videographer |
| 12:05-12:10 | Cocktail Hour | 5 minutes | Photographer& Videographer | Capture moments in events. | - Newlyweds |
| 12:10-12:15 | Guests Arrival (Reception) | 5 minutes | Staff 2, 5 and 9 | - Welcoming the Guest - Reminding guests to wear facemask and maintain social distancing. Guides the guests towards the reception hall | - Guests - Security |
| 12:15-12:20 | Newlywed Arrival (Reception) | 5 minutes | Staff 6 | Operator and Technician | Background Music “ At Last” - Newlyweds. - Photographer& Videographer |
| 12:2012:25 | First Dance | 5 minutes | Staff 6 | Operator and Technician | Background Music “All of Me” - Photographer& Videographer |
| 12:25-12:30 | The Welcome Speech | 5 minutes | Father of the Groom/Bride |  | - Microphone |
| 12:30 – 1:30 | Let’s Eat | 1 hour | Cater | Serve foods to guests. | - Food - Background Music “Jazz songs” - Photographer& Videographer |
| 1:30 – 1:40 | Cheers (Heartfelt Speeches for the Newlywed) | 10 minutes | Maid of Honor & Best Man Staff 6 | Operator and Technician | - Microphone - Background Music “Romantic Songs” - Photographer& Videographer |
| 1:40 – 1:50 | Family Dances | 10 minutes. | Event Host Staff 6 | Hosting of Events Operator and Technician | - Microphone - Background Music “Romantic Songs” - Photographer& Videographer - Newlywed - Goom Parents - Brides Parent |
| 1:50 – 2:20 | Dancing (Bouqet throw/Garter throw) | 30 minutes | Event Host Staff 6 | Hosting of Events Operator and Technician | - Microphone - Background Music “Pop Songs” - Newlywed - Bouqet/Garter - Photographer& Videographer - Guests |
| 2:20 – 2:35 | Desert Time (Cutting Ceremony) | 15 minutes | Event Host Cake Supplier Staff 6 | Hosting of Events \ Supply cake and cupcakes Operator and Technician | - Microphone - Newlywed - Cake - Photographer& Videographer - Background Music “Jazz Songs” |
| 2:35 – 3:05 | Party on | 30 minutes | Staff 6 | Operator and Technician | - Background Music “Pop/Dance Songs |
| 3:05 – 3:30 | The Grand Finale | 25 minutes | Event Host Staff 6 | Hosting of Events Operator and Technician | - Microphone - Background Music “Gratitude Songs” - Newlywed - Photographer& Videographer - Guests |

- SAMPLE INVITATION

- FRONT

- BACK

- LIST OF MENU

|  | - SET A - Flairs Catering Services | - SET B - Server’s Catering Services | - SET C - Plaza Leticia |
| --- | --- | --- | --- |
| - Buffet Lunch | - Plain Rice | - Plain Rice | - Plain Rice |
|  | - Beef Caldereta | - Calamaris | - Chicken Cordon Bleu |
|  | - Buttered Shrimp | - Beef Mushroom | - Menudo |
|  | - Chopseuy | - Chpseuy | - Beef Caldereta |
|  | - Fish Fillet | - Carbonara | - Sizzling Tofu |
|  | - Chicken Cordon Bleu | - Fried Chicken | - Buttered Shrimp |
|  | - Honey Butter Chicken | - Pork Spareribs | - Chopseuy |
|  | - Kare-Kare | - Tuna Fillet | - Pancit |
|  | - Pork Lumpia | - Pork Sisig | - Pork Lumpia |
|  | - Lechon | - Lechon | - Lechon |
| - Dessert | - Fruits | - Ice Cream | - Leche Plan |
|  | - Coffe Jelly | - Milky Gelatin | - Mango Tapioca |
| - Drinks | - Ice Tea | - Lemonade | - Pineapple Juice |
|  | - Red Tea | - Orange Juice | - Lemonade |
|  | - Water | - Water | - Water |
| - Snacks | - Club House Sandwich | - Pizza | - Fries |
|  | - Nachos | - Mini Burger | - Chees Roll |

- RISK MANAGEMENT

| RISK | CAUSE | CONTINGENCY PLAN |
| --- | --- | --- |
| Absence of Attendees | Emergency Matter | - Call/remind all participants a day before the event. - In case of absence, have a substitute for the family member |
| Running out of Food | Large number of unexpected guest | - Use Contingency Fund |
| Congested Parking | Too much vehicles | - Ensure the parking area upon confirmation of guests. - Coordinate properly for the estimated guest vehicle |
| Injury | Accident (Stampede) | - Medic/Ambulance |
| Sound System | Technical problem | - Back up sound system set |
| Brawl | People fighting | - Security/Police |